## General
Team 4 / Week 1
Mark Kaplan
Wei Lee
Timothy Park

## Progress
1. First sprint1 meeting on Feb. 12th.
2.According the tasks for user story 1 and 2, divided up the jobs as followed:
Topic | Effort | Complexity | Person
Get Google Maps API key | 1 | 1 | Timothy
Decide on folder structure, then create the appropriate folders | 1 | 2 | Mark
Setup basic HTML page using Bootstrap HTML/CSS/JS and the appropriate JavaScript libraries loaded | 1 | 2 | Wendy
Setup GitHub team & repository, then invite collaborators | 1 | 1 | Mark
Create a simple UI that has a button to run the algorithm and a display of the results | 3 | 2 | Wendy
Use Google Maps API to determine the estimated travel time between two locations | 3 | 4 | Timothy
Implement algorithm to determine the time of day / day of week that will give you the shortest estimated travel time with traffic for a given trip | 4 | 5 | Mark /Timothy
Investigate whether Google Maps API can be used with unit tests & mock data | 2 | 3 | Mark
Create a form with text fields for the start and end locations | 3 | 2 | Timothy
Connect algorithm to UI | 2 | 3 | Mark

## COTS
1. Google map API key
2. GitHub

## Defects, Problems, Concerns
Problem | Timothy dropped the class which reduces the number of available developers