## General
Team 4 / Week 7
Mark Kaplan
Wei Lee

## Progress
Task | Person | Status | Completed on | Corresponding user story
Get Google Maps API key | Mark | Complete | 2018-02-28 | 1
Decide on folder structure, then create the appropriate folders | Mark | Complete | 2018-02-15 | 1
Setup GitHub team & repository, then invite collaborators | Mark | Complete | 2018-02-13 | 1
Setup basic HTML page using Bootstrap HTML/CSS/JS and the appropriate JavaScript libraries loaded (use Starter Template) | Wei Lee | Complete | 2018-03-04 | 1
Create a simple UI that has a button to run the algorithm and a display of the results | Wei Lee | Complete | 2018-03-07 | 1
Use Google Maps API to determine the estimated travel time between two locations | Mark | Complete | 2018-03-07 | 1
Implement algorithm to determine the time of day / day of week that will give you the shortest estimated travel time with traffic for a given trip | Mark | Complete | 2018-03-14 | 1
Investigate whether Google Maps API can be used with unit tests & mock data | Mark | Complete | 2018-03-14 | N/A
Create a form with text fields for the start and end locations | Wei Lee | Complete | 2018-03-07 | 2
Connect algorithm to UI | Mark |  | 2018-03-14 | 1
Add code to show a Google Map in the web-app | Mark | Complete | 2018-03-07 | 4
Show the route on the map (either using the built-in DirectionsRenderer or by drawing it manually using Shapes or KML) | Mark | Complete | 2018-03-07 | 4
Sprint 2 planning | Mark & Wendy | Complete | 2018-04-04 | N/A
Investigate cause of Google Maps API rate limit that is lower than stated limit | Mark | In Progress |  | 1
Resolve Google Maps API rate limit issue | Mark |  |  | 1
Further investigate whether Google Maps API can be used with unit tests & mock data | Mark | In Progress |  | 1
Implement Google Maps JavaScript API Autocomplete for Addresses and Search Terms | Wendy |  |  | 3
Design an improved UI | Wendy |  |  | 2
Implement improved UI | Wendy |  |  | 2
Add additional optional form fields to UI (e.g. trip window start and end datetime, checkbox to only consider trips that start within a certain time range each day, earliest time to start trip, latest time to start trip) | Wendy |  |  | N/A
Connect additional form fields to algorithm | Mark |  |  | N/A
Add code to show a Google Map in the web-app | Mark | Complete | 2018-03-07 | 4
Show the route on the map (either using the built-in DirectionsRenderer or by drawing it manually using Shapes or KML) | Mark | Complete | 2018-03-07 | 4
Decide which library to use for graphs (of the various trip durations) | Wendy |  |  | 5
Implement the graph of the various trip durations | Wendy |  |  | 5
Implement progress bar UI element (possibly as a modal dialog) | Wendy |  |  | 6
Tie the progress bar UI element into the algorithm state | Mark |  |  | 6

## Risk
Risks
Scope of user stories in light of Timothy dropping the class
Google API rate limits made the app ran slower in the presentation.

## COTS
JavaScript
Google Maps Web Services
Google Maps JavaScript API
Bootstrap
Server Technologies
GitHub Pages (or another static website host such as Amazon S3)

## Defects, Problems, Concerns
Problem | Timothy dropped the class which reduces the number of available developers
Google Maps JavaScript API required the display of a map so tasks orig. planned for Sprint 2 had to be completed in Sprint 1
Google maps API rate limited us to a lower value than the stated limit which was making the algorithm took signifiantly more time than desired.