## General
Team 4 / Week 2
Mark Kaplan
Wei Lee

## Progress
Task | Person | Status | Corresponding user story
Get Google Maps API key | Mark | Complete | 1
Decide on folder structure, then create the appropriate folders | Mark | Complete | 1
Setup GitHub team & repository, then invite collaborators | Mark | Complete | 1
Setup basic HTML page using Bootstrap HTML/CSS/JS and the appropriate JavaScript libraries loaded | Wei Lee | In Progress | 1

## Risk
Risks
Scope of user stories in light of Timothy dropping the class

## COTS
1. Google map API key
2. GitHub

## Defects, Problems, Concerns
Problem | Timothy dropped the class which reduces the number of available developers
Wei Lee was sick this week so she was not able to work on the project