## General
Team 4 / Week 5(spring break week)
Mark Kaplan
Wei Lee

## Progress
Task | Person | Status | Corresponding user story | Completed on
Get Google Maps API key | Mark | Complete | 1 | 2018-02-28
Decide on folder structure, then create the appropriate folders | Mark | Complete | 1 | 2018-02-15
Setup GitHub team & repository, then invite collaborators | Mark | Complete | 1 | 2018-02-13
Setup basic HTML page using Bootstrap HTML/CSS/JS and the appropriate JavaScript libraries loaded (use Starter Template) | Wei Lee | Complete | 1 | 2018-03-04
Create a simple UI that has a button to run the algorithm and a display of the results | Wei Lee | Complete |  | 2018-03-07
Use Google Maps API to determine the estimated travel time between two locations | Mark | Complete | 1 | 2018-03-07
Implement algorithm to determine the time of day / day of week that will give you the shortest estimated travel time with traffic for a given trip | Mark | Complete
Investigate whether Google Maps API can be used with unit tests & mock data | Mark | Complete
Create a form with text fields for the start and end locations | Wei Lee | Complete | 2 | 2018-03-07
Connect algorithm to UI | Mark
Add code to show a Google Map in the web-app | Mark | Complete | 4 | 2018-03-07
Show the route on the map (either using the built-in DirectionsRenderer or by drawing it manually using Shapes or KML) | Mark | Complete | 4 | 2018-03-07
Today is the presentation for the first part of the project.

## Risk
Risks
Scope of user stories in light of Timothy dropping the class
Mark is sick the day beofre the project presentation
Google API rate limits made the app ran slower in the presentation.

## COTS
JavaScript
Google Maps Web Services
Google Maps JavaScript API
Bootstrap
Server Technologies
GitHub Pages (or another static website host such as Amazon S3)

## Defects, Problems, Concerns
Problem | Timothy dropped the class which reduces the number of available developers
Google Maps JavaScript API required the display of a map so tasks orig. planned for Sprint 2 had to be completed in Sprint 1
Google maps API rate limited us to a lower value than the stated limit which was making the algorithm took signifiantly more time than desired.