## General
Team 4 / Week 3
Mark Kaplan
Wei Lee

## Progress
Task | Person | Status | Corresponding user story | Completed on
Get Google Maps API key | Mark | Complete | 1 | 2018-02-28
Decide on folder structure, then create the appropriate folders | Mark | Complete | 1 | 2018-02-15
Setup GitHub team & repository, then invite collaborators | Mark | Complete | 1 | 2018-02-13
Setup basic HTML page using Bootstrap HTML/CSS/JS and the appropriate JavaScript libraries loaded (use Starter Template) | Wei Lee | Complete | 1 | 2018-03-04
Create a simple UI that has a button to run the algorithm and a display of the results | Wei Lee | Complete |  | 2018-03-07
Use Google Maps API to determine the estimated travel time between two locations | Mark | Complete | 1 | 2018-03-07
Implement algorithm to determine the time of day / day of week that will give you the shortest estimated travel time with traffic for a given trip | Mark / Timothy
Investigate whether Google Maps API can be used with unit tests & mock data | Mark
Create a form with text fields for the start and end locations | Wei Lee | Complete | 2 | 2018-03-07
Connect algorithm to UI | Mark
Add code to show a Google Map in the web-app | Mark | Complete | 4 | 2018-03-07
Show the route on the map (either using the built-in DirectionsRenderer or by drawing it manually using Shapes or KML) | Mark | Complete | 4 | 2018-03-07

## Risk
Risks
Scope of user stories in light of Timothy dropping the class

## COTS
1. Google map API key
2. GitHub

## Defects, Problems, Concerns
Problem | Timothy dropped the class which reduces the number of available developers
Google Maps JavaScript API required the display of a map so tasks orig. planned for Sprint 2 had to be completed in Sprint 1